## Total
Role | Funtionnal | Number of function | Member | Note | Start Date | End Date
Admin | crud category | 4 | Vũ
| crud customer | 4 | Vũ
| crud product | 4 | hung34
| View customer order | 1 | Hung73
| update order status - duyệt order Cancel order | 2 | Hung73
| View product details | 1 | hung 34
new 14/4 | Filter by order by order date | 1 | Minh
new 14/4 | Search product by name, category | 1 | Hung34
Dashboard of Admin | Tong doanh thu filter theo ngay thang nam | 1 | Hung73
| Orders have not approved,Total customer, total guest | 1 | Hung73
| Total customer, total guest in month | 1 | Hung73
Employee | Quản lý kho: View sản phẩm + số lượng | 1 | Kiên
| Check all order status | 1 | Minh
Customer && Guest | List all product | 1 | duong
| Filter by size | 1 | Hung73
| Filter by color | 1 | Hung73
| Sort by price | 1 | Vũ
| Search product by name | 1 | Hung73
| View product by category | 1 | Minh
| Add to cart | 1 | Hung73
| Make Order | 1 | Hung73
| View product detail | 1 | hung 34
Customer | View profile | 1 | Minh
| Update profile | 1 | Minh
| View all order và order status | 1 | Hung73
| Change password | 1 | Hung73
| Filter by order by order date | 1 | Minh | page OrderStatus
Authenticattion | Login, Logout | 1 | Hung73
| SignUp | 1 | Hùng34
| Forgot password | 1 | Hung73
Non-functional requirement | Authentication | 1 | Hung73
| Authorization | 1 | Hung73
Làm tài liêu srs |  |  | Kien |  | 2023-04-18
Làm tài liệu design |  |  | Duong |  | 2023-04-18

## Iter2
| Funtionnal | Status | Number of function
Hung73 | Filter by size, color, name | Done | 3
Hung73 | Add to cart | Done | 1
Hung73 | Make Order | Done | 1
Hung73 | View all order và order status | Done | 1
Hung73 | Admin: view order, duyệt order, Cancel order | Done | 3
Vũ(bỏ delete customer và create customer, thay bằng edit status customer) | create category | Done | 1
Vũ | delete category | Done | 1
Vũ | update category | Done | 1
Vũ | view category | Done | 1
Vũ | create customer | Done | 1
Vũ | view customer | Done | 1
Vũ | edit customer | Done | 1
Vũ | delete customer | Done | 1
Minh | View profile | Done
Minh | Update profile | Done
Minh | Customer: Filter by order by order date | Done
Hung34 | create Product | Done
Hung34 | delete Product | Done
Hung34 | update Product | Done
Hung34 | view Product | Done
Hung34 | View product detail | Done

## Iter3
Member | Funtionnal | Status | Number of function |  | Hoàn thiện hết các chức năng
Hung73 | Change password | Complete | 1 |  | Chỉnh sửa lại layout front-end
Hung73 | Forgot password | Complete | 1
Hung73 | Tổng Orders in month in years | Complete | 1
Hung73 | Orders chưa duyệt, Tổng Orders, Tổng Customers, Tổng Guest | Complete | 1
Hung73 | Tổng Customers, Tổng Guest mỗi tháng | Complete | 1
Minh | Admin: Filter by order by order date | Complete |  | Tham khảo code phần list all order của Customer
Minh | Employee: Check all order status(không duyệt được hàng) | Complete
Kiên | Làm srs | In Progress
Duong, Hùng34 | Làm sds
Vũ | Authenticate | In Progress
Vũ | Authorization | In Progress

## Iter4
Task | Member | Note
Test Bug | All
Update front-end: chỉnh lại cụm search, filter cho đẹp hơn | Hung34
Phần authenticate vs authorization | All.
Làm slide present | Hung73
Hoàn thiện chức năng edit customer | Vu
Chạy lại sql ở inter3-final--> Add lại trong database --> product có ảnh khi list all product ở project | Vu
Show product details có nhiều ảnh của nó | Hung34
Thêm link forgot password ở sign in | Hung73
SRS done 100% | Kien
SDS done 100% | Duong
Monitor progess | Hung73

## Question
Member | Question | Date