## Issue Report
Project | Sneaker Online Shop
Manager
Issue No | Status | Description | Type | Priority | Assignee | Raised By | Open | Close | Comment
1 | Fixed | Session will be lost when user accessed login page | Problem | High | DuongNH | HungLM_73 | 2023-04-11 | 2023-04-16 | No comment
2 | Fixed | Links from one site to another don't work | Problem | High | VuVT | HungLM_34 | 2023-04-12 | 2023-04-13 | No comment
3 | Fixed | Entering a large amount of data causes the program to fail | Problem | High | HungLM_34 | MinhNN | 2023-04-15 | 2023-04-04 | No comment
4 | Fixed | Layout is broken when opening to different environments (browser) | Problem | High | MinhNN | HungLM_73 | 2023-04-16 | 2023-04-19 | No comment
5 | Fixed | Do not display or display incorrect error messages when input errors occur on the screen | Problem | Medium | KienNN | VuVT | 2023-04-16 | 2023-04-17 | No comment
6 | Fixed | Local host not deployed | Problem | Low | DuongNH | MinhNN | 2023-04-17 | 2023-04-17 | Each computer have a different locol host port example: loacalhost 8080, locahost 9999
7 | Fixed | Navigation bar in other web page cannot use search feature | Problem | Medium | HungLM_73 | VuVT | 2023-04-18 | 2023-04-19 | Each web page have default value to search, must pass to other page use search feature
8 | Fixed | User infomation can be display without login with the link | Problem Unsecurity | High | VuVT | HungLM_34 | 2023-04-20 | 2023-04-22 | Add filter for user information
9 | Fixed | Cannot send email to any services | Problem | Medium | HungLM_34 | HungLM_73 | 2023-04-21 | 2023-04-23 | Use public address to access network